## Sheet1
EasyA Software Project
| Project Timeline as of: | 2024-01-14
| The timeline is maintained by: | Entire Team
| Team Members: | SB: Simone Badaruddin
EC: Erin Cohen
|  | IC: Isabella Cortez | [15 empty] | Today
ND: Nithi Deivanayagam
LM: Luke Marshall
|  |  | Expected Days | January | [30 empty] | February | [27 empty] | March
Tasks and Milestones |  | Assigned to... | time axis 2022-01-01 to 2022-03-16
Project Planning
| Assemble team. | Entire Team | 4
| Initial brainstorm and assigning of tasks. | Entire Team | 1
| All team members sign off on initial timeline. | Entire Team | 0
...
Requirements Analysis
| Read papers on global weather tracking. | NK, ML, JS | 4
| Deliver reports on papers that were read. | Entire Team | 1
| Schedule with subject matter experts (SMEs) | ML, WZ | 8 (part time)
| Interview SMEs. | ML, WZ | 5
| Review existing weather tracking software. | NK, JS | 4
| Distill major requirements from interviews and research | Entire Team | 4
| Write initial SRS. | NK, JS | 2
| Review initial SRS with stakeholders | ML, WZ | 2
...
Design
...
Implementation
...
| Distill major requirements from interviews and research | Entire Team
Testing
...
Note that there are other ways to organize
the tasks other than by major project activity,
such as by software module.
Key
The tall rows show when the task was planned to be worked on and completed.
The short rows show when the task was actually worked on and completed.
Planned activity.
Milestone at the end of a planned activity.
Slippage.
How time was actually spent.
When a milestone was actually achieved.