## Sheet1
Tasks and Assignment Breakdown
| Group: | <group name>
| Team Members (and initials): | Simone Badaruddin (SB), Erin Cohen, Isabella Cortez, Nithi Deivanayagam, Luke Marshall
| Date this was last updated: | 2023-01-14
| Last updated by (whom): | SB
Grouping | Task or Milestone (with an objectively verifiable completion) | Status | Assigned to (whom) | Date Assigned | Anticipated Time (hours) | Date Due | Date Completed | Completed by (whom) | Time Spent (hours) | Confirmed Completed by (whom) | Date Confirmed Complete | Notes
Week 1
| Establish weekly meeting schedule. Post on shared repository. | completed | all staff
Write up summary of client meeting. Post on shared repository.
| Group meeting. |  | all staff |  |  |  |  | (whoever attended)
Week 2
| Generate v1 of SDS. Post on shared repository. | not yet completed
Note that the following provides an alternative grouping, by project activity rather than by week.
Requirements
Have initial meeting with client to review v1 of SRS.
Write up summary of client meeting. Post on shared repository
Design
Generate v1 of SDS. Post on shared repository.
...
Project Planning
Establish weekly meeting schedule. Post on shared repository.
Week 1 Group Meeting 1.
Week 1 Group Meeting 2.